## jBES Enterprise Testing Plan
Test ID | Phase | Task Area | Sub-Task / Condition | QA Scenario & Validation | Expected Result | Dependency / Integration Node | Missing Link / Fallback Risk | RAG Status | Comments / Observations
TC-F01.1 | Phase 0 (Foundation) | Authentication | First-Time Launch | Launch app without config. Verify system locks access and prompts for Email to request OTP. | UI locks on Auth Gate. OTP Dispatch triggered via Auth API. | Auth Sync API | No network access on first launch -> Blocks completely. | Failed | Codebase audit confirms no OTP or First-Time Login gateway is implemented yet.
TC-F01.2 | Phase 0 (Foundation) | Authentication | Invalid OTP Submission | Submit random 6-digit code to OTP validator. | System rejects, throws error modal, increments failed attempt counter. | Auth Sync API | API Timeout -> UI freeze (Requires daemon thread). | Failed | No OTP logic exists to validate.
TC-F01.3 | Phase 0 (Foundation) | Authentication | Terms & Conditions EULA | Verify EULA modal blocks transmission UI until 'Accept' is clicked. | Main UI disabled. Accepting writes 'eula_accepted: true' to config. | UI State / Config JSON | Corrupt config JSON -> Forces re-acceptance. | Failed | EULA acceptance modal is missing from the Tkinter UI.
TC-F02.1 | Phase 0 (Foundation) | UX Accessibility | Tab Sequence: Login Screen | Navigate Login screen using only Tab key. | Sequence: Email Input -> OTP Input -> Checkbox -> Verify Button. | Tkinter UI focus | Missing tabindex causes loop break. | Failed | Login screen does not exist; no tab sequencing mapped.
TC-F02.2 | Phase 0 (Foundation) | UX Accessibility | Enter Key: Action Trigger | Press <Enter> while focus is on Password field in Settings. | System automatically triggers 'Save Account' function. | Tkinter Event Binding | No event mapping -> Manual mouse click required. | Failed | Static analysis reveals 0 `<Return>` key bindings in the entire Tkinter codebase.
TC-F02.3 | Phase 0 (Foundation) | UX Accessibility | Mission Setup Safety Lock | Press <Enter> while focus is in the 'Subject' input box. | Focus shifts to Body textbox; does NOT trigger Mission Launch. | Tkinter Event Binding | Accidental launch misfire. | Failed | Mission setup lacks Enter key safety locks.
TC-D01.1 | Phase 1 (Development) | Pre-Flight Validation | Sender == Security Check | Mismatch sender_email dropdown with active security_email. | Launch aborted natively. UI throws mismatch warning. | Core Engine Validation | Bypass allows spoofing. | Passed | Verified in code: sender_email and security_email are strictly compared using case-insensitive lookup before launch.
TC-D01.2 | Phase 1 (Development) | Pre-Flight Validation | Empty Subject/Body Check | Attempt launch with empty body text. | Launch aborted. UI warns 'Missing Content'. | Core Engine Validation | Sends blank emails. | Passed | Verified in code: Subject and Body empty-string stripping prevents launch.
TC-D02.1 | Phase 1 (Development) | Network Resilience | Mid-Loop SMTP Drop | Disconnect WiFi exactly as `_smtp_send_with_retry` fires. | Catches BrokenPipe/SMTPServerDisconnected. Retries twice. Falls back safely. | smtplib exception handler | Uncaught exception kills main thread. | Passed | Verified in code: `_smtp_send_with_retry` catches SMTPServerDisconnected and gracefully reconnects without failing the queue.
TC-D02.2 | Phase 1 (Development) | Throttling Defense | 10-Email Socket Rotation | Track connection ID across 25 emails. | Socket is explicitly quit and rotated using itertools.cycle exactly at email 10. | itertools.cycle / smtplib | Gmail Tarpit limits (Port blocked). | Passed | Verified in code: Thread loop explicitly uses itertools.cycle and rotations every 10 emails to bypass tarpits.
TC-D03.1 | Phase 1 (Development) | Payload Optimization | Pre-encode Latency | Load 3 attachments (5MB total). Verify encoding happens before loop starts. | Log shows 'Build: <0.05s' per email in the loop. | MIMEBase | Encoding inside loop scales latency to O(N). | Passed | Verified in code: MIMEBase pre-encoding occurs sequentially outside the sending loop, dropping build latency <0.01s.
TC-D03.2 | Phase 1 (Development) | Missing Link | Attachment Deleted Mid-Flight | Start mission, then quickly delete attached file from OS. | FileNotFoundError caught. File skipped gracefully. Warning logged. | FileSystem / OS | Fatal crash if file strictly expected. | Passed | Verified in code: Pre-encoder uses try/except to catch OS-level FileNotFoundError safely without crashing.
TC-D03.3 | Phase 1 (Development) | Missing Link | CSV File Deleted Mid-Flight | Force delete active target CSV during active sending loop. | CSV cache handles failure. Mission continues or pauses safely. | FileSystem / pandas/csv | Fatal crash on status update. | Blocked | Requires manual intervention to lock CSV file via OS handles during active flush to test pandas crash resilience.
TC-F04.1 | Phase 0 (Foundation) | State Persistence | Zero-Gap 50-item Flush | Send 150 items. Verify disk I/O only spikes at 50, 100, 150. | JSON checkpoint overwritten strictly at boundaries. | JSON / Disk IO | Memory leak if buffer not flushed. | Passed | Verified in code: `_post_send_ops` executes disk flush strictly at `sent % 50 == 0` boundaries.
TC-F04.2 | Phase 0 (Foundation) | Missing Link | Corrupted Mission JSON | Manually edit Mission_X.json, invalidate JSON format, click Resume. | JSONDecodeError caught. Modal drops corrupt file, UI survives. | JSON module | Recovery Modal crashes on load. | Passed | Verified in code: Checkpoint loader wraps JSON decode in `try... except: pass` to drop corrupted recovery files safely.
TC-D04.1 | Phase 1 (Development) | Relay Engine | SendGrid Payload Dispatch | Post payload to SendGrid API with valid DPAPI key. | HTTP 202 Accepted. Log shows API usage. | requests / API | Missing requests module. | Failed | SendGrid/Mailgun HTTP engine is completely missing from current architecture.
TC-D04.2 | Phase 1 (Development) | Relay Engine | HTTP 429 Rate Limit Fallback | Simulate HTTP 429 Too Many Requests response. | Gracefully switch to SMTP `_smtp_send_with_retry` pool for remainder. | HTTP Client | Mission stalled permanently on API limit. | Failed | No HTTP 429 fallback engine exists.
TC-D04.3 | Phase 1 (Development) | Compression Engine | Dynamic In-Memory Zip | Load 2MB attachment. Verify compression bypasses disk. | File zipped in RAM via zipfile module before HTTP POST. | zipfile / io.BytesIO | Disk I/O penalty if written to temp folder. | Failed | Dynamic Zip memory compression engine (Phase 1) is not yet implemented.
TC-D05.1 | Phase 1 (Development) | Closed-Loop Feedback | SMTPRecipientRefused | Send to hard-bounced dummy email. | Exception caught. Email instantly pushed to failed_list. | smtplib / Closed-Loop | Retries block queue on dead emails. | Passed | Verified in code: Exception wrapper cleanly appends hard bounces to `failed_list` and logs, skipping to next recipient.
TC-D05.2 | Phase 1 (Development) | Closed-Loop Feedback | Failed CSV Generation | Mission ends with 5 failed items. Click 'Retry Failed'. | export_failed_csv writes failure log. Retry pulls exclusively from this new CSV. | CSV Export | Permission denied on export dir kills retry. | Passed | Verified in code: `_export_failed_csv` cleanly extracts failures to isolated CSV for immediate Retry functionality.