## jBES Enterprise Testing Plan
Test ID | Phase | Task Area | Sub-Task / Condition | QA Scenario & Validation | Expected Result | Dependency / Integration Node | Missing Link / Fallback Risk | RAG Status | Comments / Observations
TC-F01.1 | Phase 0 | Authentication | First-Time Launch | Launch app without config. Verify system locks access and prompts for Email to request OTP. | UI locks on Auth Gate. | Auth Sync API | No network access on first launch -> Blocks completely. | Passed | OTP Gateway dynamically intercepts first boot. Test 2026-06-03 00:01:31
TC-F01.2 | Phase 0 | Authentication | Invalid OTP Submission | Submit random 6-digit code to OTP validator. | System rejects, throws error. | Auth Sync API | API Timeout -> UI freeze. | Passed | 6-digit regex enforces OTP verification. Test 2026-06-03 00:01:31
TC-F01.3 | Phase 0 | Authentication | Terms & Conditions EULA | Verify EULA modal blocks transmission UI until 'Accept' is clicked. | Main UI disabled. | UI State | Corrupt config JSON -> Forces re-acceptance. | Passed | EULA modal successfully blocks UI until Accepted. Test 2026-06-03 00:01:31
TC-F02.1 | Phase 0 | UX Accessibility | Tab Sequence: Login Screen | Navigate Login screen using only Tab key. | Sequence matches input flow. | Tkinter UI focus | Missing tabindex causes loop break. | Passed | Tkinter traversal sequencing allows Tab key mapping. Test 2026-06-03 00:01:31
TC-F02.2 | Phase 0 | UX Accessibility | Enter Key: Action Trigger | Press <Enter> while focus is on Password field. | Triggers save_account. | Tkinter Event Binding | Manual mouse click required. | Passed | Return (<Enter>) key explicitly bound to save_config and OTP validation. Test 2026-06-03 00:01:31
TC-F02.3 | Phase 0 | UX Accessibility | Mission Setup Safety Lock | Press <Enter> in Subject input box. | Does NOT trigger Mission Launch. | Tkinter Event Binding | Accidental launch misfire. | Passed | Enter key safely disabled on Launch button to prevent misfires. Test 2026-06-03 00:01:31
TC-D01.1 | Phase 1 | Pre-Flight Validation | Sender == Security Check | Mismatch sender_email dropdown with active security_email. | Launch aborted natively. | Core Engine Validation | Bypass allows spoofing. | Passed | Sender==Security exact string matching enforced. Test 2026-06-03 00:01:31
TC-D01.2 | Phase 1 | Pre-Flight Validation | Empty Subject/Body Check | Attempt launch with empty body text. | Launch aborted. | Core Engine Validation | Sends blank emails. | Passed | Subject/Body null check enforced. Test 2026-06-03 00:01:31
TC-D02.1 | Phase 1 | Network Resilience | Mid-Loop SMTP Drop | Disconnect WiFi exactly as _smtp_send_with_retry fires. | Retries twice. Falls back safely. | smtplib exception handler | Uncaught exception kills main thread. | Passed | SMTPServerDisconnected gracefully resets socket. Test 2026-06-03 00:01:31
TC-D02.2 | Phase 1 | Throttling Defense | 10-Email Socket Rotation | Track connection ID across 25 emails. | Socket rotates at email 10. | itertools.cycle | Port blocked by ISP. | Passed | Socket rotated via itertools.cycle. Test 2026-06-03 00:01:31
TC-D03.1 | Phase 1 | Payload Optimization | Pre-encode Latency | Load 3 attachments (5MB total). | Build time < 0.05s per email. | MIMEBase | Encoding scales latency to O(N). | Passed | MIMEBase encoding occurs sequentially outside payload loop. Test 2026-06-03 00:01:31
TC-D03.2 | Phase 1 | Missing Link | Attachment Deleted Mid-Flight | Delete attached file from OS mid-loop. | File skipped gracefully. | FileSystem | Fatal crash if expected. | Passed | FileNotFoundError safely caught. Test 2026-06-03 00:01:31
TC-D04.1 | Phase 1 | Relay Engine | SendGrid Payload Dispatch | Post payload to SendGrid API. | HTTP 202 Accepted. | requests / API | Missing requests module. | Passed | APIRelayEngine intercepts payload and routes HTTP via SendGrid v3. Test 2026-06-03 00:01:31
TC-D04.2 | Phase 1 | Relay Engine | HTTP 429 Rate Limit Fallback | Simulate HTTP 429 Too Many Requests response. | Graceful switch to SMTP pool. | HTTP Client | Mission stalled. | Passed | HTTP 429 explicitly caught, triggers SMTP Fallback natively. Test 2026-06-03 00:01:31
TC-D04.3 | Phase 1 | Compression Engine | Dynamic In-Memory Zip | Load 2MB attachment. | File zipped in RAM via zipfile. | zipfile | Disk I/O penalty. | Passed | ZipManager auto-compresses files > 1MB via io.BytesIO. Test 2026-06-03 00:01:31
TC-D06.1 | Phase 1 | Dependency Audit | Requests Module Missing | Launch SendGrid payload on clean machine without 'requests' installed. | ImportError catches safely, flags bypass. | pip / requests | Engine catastrophic failure. | Passed | ImportError safely caught and bypasses HTTP engine natively. Test 2026-06-03 00:01:31
TC-D06.2 | Phase 1 | Memory Missing Link | RAM Exhaustion via massive file | Attach 250MB video file. ZipManager triggers read(). | 25MB cap triggers bypass; memory protected. | io.BytesIO / Memory | OOM (Out Of Memory) hard crash. Missing 25MB cap. | Passed | ZipManager successfully caps memory footprint at 25MB. Test 2026-06-03 00:01:31
TC-D06.3 | Phase 1 | Integration Logic | HTTP 401 Unauthorized API Key | Inject invalid SendGrid API Key. | Raises Exception, falls back natively to SMTP pool. | HTTP Status Codes | Fails to fallback to SMTP. | Passed | Universal Exception fallback successfully triggers SMTP routing on 401 errors. Test 2026-06-03 00:01:31
TC-F03.1 | Phase 0 | Integration Logic | Premature Config Save (Boot) | Check Auth Gate saves config before UI initializes variables. | hasattr() protects sendgrid_key_var from crashing app. | Config JSON Lifecycle | UI elements queried before instantiation. | Passed | hasattr() validation protects early save_config cycles. Test 2026-06-03 00:01:31
TC-W01.1 | Phase 2 - Frontend | API Validation | Next.js JSON Payload Structural Integrity | Submit bulk email form from React UI with nested attachments array. | FastAPI accepts 200 OK. Pydantic validation passes. | Frontend-Backend REST API | Malformed JSON crashes backend. | Pending | AWS Migration Blueprint: Validate REST structures.
TC-W01.2 | Phase 2 - Frontend | Web Sockets | WebSocket Event Disconnect | Sever frontend internet connection mid-transmission. | FastAPI catches disconnect, continues server-side mission, logs state for reconnect. | Socket.io / FastAPI | Server thread dies when client disconnects. | Pending | AWS Migration Blueprint: Async state retention.
TC-W01.3 | Phase 2 - Frontend | UI Due Diligence | Cross-Browser Flexbox Rendering | Load Shadcn/UI Dashboard on Chrome, Safari, Firefox mobile. | 100% Responsive Flexbox Grid. | CSS / Tailwind | Layout breaks on mobile Safari. | Pending | AWS Migration Blueprint: Visual layout audits.
TC-W02.1 | Phase 2 - Backend | Missing Links | Local File System to Cloud S3 | Attempt to attach a local file path inside the Web App. | FastAPI safely intercepts and requests Boto3 S3 pre-signed URL instead. | os.path vs Boto3 | Server crashes looking for C:\ drive files. | Pending | AWS Migration Blueprint: Missing Link File System protection.
TC-W02.2 | Phase 2 - Backend | Dependency Chain | FastAPI to SMTP Legacy Loop | Trigger the legacy `_smtp_send_with_retry` loop from a REST endpoint. | Legacy Python generator function yields successfully to Async REST endpoint. | Python asyncio vs threading | Deadlock caused by blocking legacy thread. | Pending | AWS Migration Blueprint: Async dependency integration.
TC-W03.1 | Phase 2 - Database | PostgreSQL Drops | PostgreSQL Connection Timeout | Force drop PostgreSQL connection mid-authentication. | Web App fails gracefully, prompts user to retry, doesn't leak JWT. | SQLAlchemy / Prisma | Stack trace leaks DB credentials. | Pending | AWS Migration Blueprint: Database resilience.
TC-W03.2 | Phase 2 - Database | Redis Eviction | Redis Cache Memory Exhaustion | Flood Redis with 100,000 live mission log lines. | Redis LRU eviction triggers; old logs pruned safely. | Redis Server | Redis OOM crash brings down WebSocket. | Pending | AWS Migration Blueprint: Memory safety for Live Logs.
TC-W03.3 | Phase 2 - Database | AWS S3 Missing Link | Deleted S3 Object Mid-Mission | Delete CSV file from AWS S3 while FastAPI is reading it. | FastAPI gracefully catches 404 from S3 and aborts batch, saving state. | Boto3 AWS SDK | Hard 500 Server Error. | Pending | AWS Migration Blueprint: S3 Object state protection.
TC-W04.1 | Phase 2 - QA Security | JWT Auth | JWT Token Expiration Validation | Attempt to fire API dispatch with a 2-hour expired JWT token. | HTTP 401 Unauthorized. React auto-redirects to Login. | AWS Cognito / JWT | Unauthenticated SMTP abuse. | Pending | AWS Migration Blueprint: Zero-trust architecture token validation.
TC-W05.1 | Phase 2 - Mode Setup | Online Mode | First-Launch Path Creation | Choose Online Mode and confirm setup. | Directories ~/jBulkEmail/data and ~/jBulkEmail/webservice are successfully created. | OS File System | Parent directory lacks write permissions. | Pending | AWS Migration Blueprint: Check permissions and create paths.
TC-W05.2 | Phase 2 - Mode Setup | Local Mode | Local System Dependency Install | Choose Local System Mode and click confirm. | Downloads the jBulkEmail zip from GitHub, extracts packages to ~/jBulkEmail, and registers core. | urllib / zipfile | GitHub API rate-limited or offline. | Pending | AWS Migration Blueprint: Download recovery fallback.